## Payroll System Consultant Log T
Issue | Status | Logged On | Closed On | Logged By | Assigned To | Environment | Module | Action/Process | Issue Description | fix description
Develop the GL Mapping Module | Fixed | 2025-07-28 | 2025-08-11 | Martin Mwale | Simon Chiwamba | UAT | Payroll GL Journal | Claims Processing | module is intended to manage the processing of claims approved in the HR system | Approved Claims processing module fully implemented in the payroll system
Complete and balance Payroll JV exports
The payslip vairables must sorted by code
The payroll dumb must be sorted by code
Generate 438 report - Earnings by Cost Centre
The payslip vairables must sorted by code
The payroll dumb must be sorted by code

## Payroll Staff Log Tab
S/n | Description | Responsible Office | Problems/ issues | Comment
1 | Basic Pay | CICT | - The system only has one basic pay for all the employees - The Basic pay is attached to all employees regardless of the contract type. | - This makes reporting difficult. - Basic pay and other allowances should be Categorised This risk overpaying Staff without valid contracts
2 | Bulk upload | CICT | Not working on over time.The system does not have a data capture platform where mass data can be captured.This is a key function to this payroll | - Bulk upload is not working on over time. We process more than 150 transactions on the monthly basis
3 | Report Module | CICT | Not working as expected | - Payroll register is not printing - Earnings Report not complete - Refer to the Payroll summary report - Payroll JV is not printing or being extracted - Nhima and napsa employer contribution is not visible
4 | Operation | CICT | -The system is not easy to use The system require transactions to be captured 1 by 1.This is not practical as we are dealing with more than 2000 employees | - The system is not user friendly - Refer to the process of posting over time, excess and other allowances